## README
How this version works
The file works in this flow:
Product_Registry → Project_Tracker → Dashboard / BOM_Tracker / Comments_Log
So the normal habit should be:
create or update the project in Product_Registry
let Project_Tracker generate the dates
check the schedule in Dashboard
manage purchasing in BOM_Tracker
record issues in Comments_Log
2) Product_Registry
This is your master project list.
What you should do here
For each new project, add one row and fill in the main project details:
A: Tag No.
B: Description
C: Product Type
D: Customer
E: Contract Signed
F: ROS
G: Contract No.
H: Sales Ref
I: Project Manager
J: Engineer Owner
K: Procurement Owner
L: Production Owner
M: FAT Owner
N: Notes 3) Project_Tracker
This is the main scheduling engine.
It calculates the milestone dates based on the project data and the logic rules.
What you should input
For each active project row, you can key in either:
Column A: Tag No. or
Column B: Description
Once one of those matches the master data, the sheet resolves the project and fills the rest automatically.
What fills automatically
These columns are generated:
product type
customer
owners
contract date
ROS
milestone dates:
  Level 1 Plan
  Input Frozen
  Drawing Approval
  BOM Pass to PR
  PR Schedule
  Components PO Plan
  Production Start
  Production Complete
  NOI Date
  Internal Test Start / Complete
  FAT Start / Complete
  Delivery
It also calculates:
Overall Status
Days to ROS
What you can manually update here
These are meant for working updates:
AB: Level 1 No.
AC: BOM No.
AD: PR No.
AE: NOI No.
AF: Delivery Actual / ETA
AG: Arrival Status
AJ: Notes
Best way to use it
After adding a project in the registry:
type the tag number in column A here or
paste the description in column B
Then review the generated dates.
Important
Do not overwrite the formula columns from C onward unless you intentionally want to redesign the workbook.
4) Dashboard
This is the visual reporting page.
It is mainly for viewing, not for building the data.
How to use it
Go to cell A6 and enter the Tag No. of the project you want to see.
Once you do that, the page updates:
description
customer
product type
ROS
production start
PO planning date
phase status table
daily Gantt chart
5) Logic & Lists
This is the rules page.
You only touch this page when you want to change the standard planning logic.
It has 3 main parts.
A. Milestone Logic by Product Type
This section defines how dates are calculated.
For each product type, the sheet stores:
milestone name
anchor / basis
offset in days
note
Example:
Production Start = Production Complete minus 45 days
Delivery = ROS minus 3 days
How it works
If your project’s product type exists in this table, that logic is used. If not, the workbook uses Default.
B. Procurement Lead Times
This section stores the standard lead time for each of the 17 BOM components.
Examples:
compressor
evaporator
condenser
cables
insulation
etc.
These lead times drive the BOM_Tracker.
C. Validation / preview area
There is also a helper area showing:
selected tag
selected project procurement preview
latest PO/prep dates
This is mainly for checking the logic.
When to edit this page
Edit it only when:
standard milestone timing changes
production duration changes
procurement lead times change
a new product type needs its own rule set
6) BOM_Tracker
This is the procurement control page.
It expands each project into a fixed list of component lines.
How it works
Each project gets 17 component rows.
For each row, the sheet auto-calculates:
tag no.
description
product type
arrival deadline
component
lead time
latest PO / prep by date
days until needed
urgency
Urgency is auto-labeled as
OK
PREPARE
URGENT
OVERDUE
ORDERED
What you should manually update here
These are the working fields:
K: Actual PO Date
M: Vendor
N: PO No.
O: Notes
7) Comments_Log
This is the manual action log.
What to fill in
Date
Tag No.
Owner
Update Type
Issue / Status
Comment
Next Action
Follow-up Date
Best use
Use this for:
delay reasons
design freeze changes
vendor issues
FAT changes
customer comments
action follow-up
This is useful when the schedule shows risk but you also need the reason and next step.

## Dashboard
冷水机组 Delivery Dashboard
Master dashboard linked to Product_Registry, Project_Tracker, Logic & Lists, and BOM_Tracker.
Selected Tag |  | Description |  | Customer | Product Type |  | ROS |  | Production Start |  | Components PO Plan |  | Days to ROS |  | Urgent BOM Items |  | Project Manager |  | Overall Status
123456 |  | Chiller Water Unit |  | Sample Customer | 冷水机组 |  | 2026-10-20 |  | 2026-08-10 |  | 2026-03-23 |  | 63 |  | 17 |  | PM Owner |  | On Track
Phase status table |  |  |  |  | Program Timeline / Daily Phase Gantt
Phase | Plan Start | Plan Finish | Reference | Status | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct
 | time axis 2026-02-01 to 2026-10-28
Contract / Kickoff | 2026-03-10 | 2026-04-07 | CN-2026-001 | Done | bar: 2026-02-01 to 2026-10-28
Drawing Freeze | 2026-02-21 | 2026-03-13 | Input Frozen → Drawing Approval | Done | bar: 2026-02-01 to 2026-10-28
BOM Release | 2026-03-13 | 2026-03-20 | Drawing Approval → BOM Pass | Done | bar: 2026-02-01 to 2026-10-28
PR / PO Planning | 2026-03-16 | 2026-03-23 | PR Schedule → Components PO Plan | Done | bar: 2026-02-01 to 2026-10-28
Material Lead Time | 2026-03-23 | 2026-08-10 | Components PO Plan → Production Start | Done | bar: 2026-02-01 to 2026-10-28
Production | 2026-08-10 | 2026-09-24 | Production Start → Complete | Current | bar: 2026-02-01 to 2026-10-28
NOI / Docs | 2026-09-04 | 2026-10-02 | NOI Date → FAT Start | Planned | bar: 2026-02-01 to 2026-10-28
Internal Test | 2026-09-27 | 2026-09-30 | Internal Test Start → Complete | Planned | bar: 2026-02-01 to 2026-10-28
FAT | 2026-10-02 | 2026-10-09 | FAT Start → Complete | Planned | bar: 2026-02-01 to 2026-10-28
Delivery / ROS | 2026-10-17 | 2026-10-20 | Delivery → ROS | Planned | bar: 2026-02-01 to 2026-10-28
Select a Tag No. in A6. The daily phase Gantt updates automatically from the linked sheets.
Contract Signed | 46091
Level 1 Plan | 46119
Input Frozen | 46074
Drawing Approval | 46094
BOM Pass to PR | 46101
PR Schedule | 46097
Components PO Plan | 46104
Production Start | 46244
Production Complete | 46289
NOI Date | 46269
Internal Test Start | 46292
Internal Test Complete | 46295
FAT Start | 46297
FAT Complete | 46304
Delivery | 46312
ROS | 46315
Formulas:
Customer = IF([Description]="","",IF(TODAY()>[Description],"Done",IF(TODAY()<B12,"Planned","Current")))

## Project_Tracker
TAG NO. | DESCRIPTION | PRODUCT TYPE | CUSTOMER | CONTRACT SIGNED | ROS | CONTRACT NO. | SALES REF | PROJECT MANAGER | ENGINEER OWNER | PROCUREMENT OWNER | PRODUCTION OWNER | FAT OWNER | LEVEL 1 PLAN | INPUT FROZEN | DRAWING APPROVAL | BOM PASS TO PR | PR SCHEDULE | COMPONENTS PO PLAN | PRODUCTION START | PRODUCTION COMPLETE | NOI DATE | INTERNAL TEST START | INTERNAL TEST COMPLETE | FAT START | FAT COMPLETE | DELIVERY | LEVEL 1 NO. | BOM NO. | PR NO. | NOI NO. | DELIVERY ACTUAL / ETA | ARRIVAL STATUS | OVERALL STATUS | DAYS TO ROS | NOTES | TYPE KEY | RESOLVED TAG | RESOLVED DESCRIPTION
123456 | Chiller Water Unit | 冷水机组 | Sample Customer | 2026-03-10 | 2026-10-20 | CN-2026-001 | P84 Pilot | PM Owner | Engineering Owner | Procurement Owner | Production Owner | QA / FAT Owner | 2026-04-07 | 2026-02-21 | 2026-03-13 | 2026-03-20 | 2026-03-16 | 2026-03-23 | 2026-08-10 | 2026-09-24 | 2026-09-04 | 2026-09-27 | 2026-09-30 | 2026-10-02 | 2026-10-09 | 2026-10-17 | [6 empty] | On Track | 63 |  | 冷水机组 | 123456 | Chiller Water Unit
This sheet is auto-linked from Product_Registry. Edit only the white manual fields: reference numbers, delivery actual / ETA, arrival status, and notes.
Formulas:
CONTRACT SIGNED = IF([RESOLVED TAG]="","",IFERROR(INDEX(Product_Registry!$E2:E101,MATCH([RESOLVED TAG],Product_Registry!$A2:A101,0)),""))
ROS = IF([RESOLVED TAG]="","",IFERROR(INDEX(Product_Registry!$F2:F101,MATCH([RESOLVED TAG],Product_Registry!$A2:A101,0)),""))
LEVEL 1 PLAN = IF([RESOLVED TAG]="","",[CONTRACT SIGNED]+SUMIFS('Logic & Lists'!$E4:E200,'Logic & Lists'!$A4:A200,[TYPE KEY],'Logic & Lists'!$C4:C200,"Level 1 Schedule"))
INPUT FROZEN = IF([RESOLVED TAG]="","",[DRAWING APPROVAL]+SUMIFS('Logic & Lists'!$E4:E200,'Logic & Lists'!$A4:A200,[TYPE KEY],'Logic & Lists'!$C4:C200,"Input Frozen"))
DRAWING APPROVAL = IF([RESOLVED TAG]="","",[BOM PASS TO PR]+SUMIFS('Logic & Lists'!$E4:E200,'Logic & Lists'!$A4:A200,[TYPE KEY],'Logic & Lists'!$C4:C200,"Drawing Approval"))
BOM PASS TO PR = IF([RESOLVED TAG]="","",[COMPONENTS PO PLAN]+SUMIFS('Logic & Lists'!$E4:E200,'Logic & Lists'!$A4:A200,[TYPE KEY],'Logic & Lists'!$C4:C200,"BOM Pass to PR"))
PR SCHEDULE = IF([RESOLVED TAG]="","",[COMPONENTS PO PLAN]+SUMIFS('Logic & Lists'!$E4:E200,'Logic & Lists'!$A4:A200,[TYPE KEY],'Logic & Lists'!$C4:C200,"PR Schedule"))
COMPONENTS PO PLAN = IF([RESOLVED TAG]="","",[PRODUCTION START]+SUMIFS('Logic & Lists'!$E4:E200,'Logic & Lists'!$A4:A200,[TYPE KEY],'Logic & Lists'!$C4:C200,"Components PO Plan"))
PRODUCTION START = IF([RESOLVED TAG]="","",[PRODUCTION COMPLETE]+SUMIFS('Logic & Lists'!$E4:E200,'Logic & Lists'!$A4:A200,[TYPE KEY],'Logic & Lists'!$C4:C200,"Production Start"))
PRODUCTION COMPLETE = IF([RESOLVED TAG]="","",[INTERNAL TEST START]+SUMIFS('Logic & Lists'!$E4:E200,'Logic & Lists'!$A4:A200,[TYPE KEY],'Logic & Lists'!$C4:C200,"Production Complete"))
NOI DATE = IF([RESOLVED TAG]="","",[FAT START]+SUMIFS('Logic & Lists'!$E4:E200,'Logic & Lists'!$A4:A200,[TYPE KEY],'Logic & Lists'!$C4:C200,"NOI Date"))
INTERNAL TEST START = IF([RESOLVED TAG]="","",[INTERNAL TEST COMPLETE]+SUMIFS('Logic & Lists'!$E4:E200,'Logic & Lists'!$A4:A200,[TYPE KEY],'Logic & Lists'!$C4:C200,"Internal Test Start"))
INTERNAL TEST COMPLETE = IF([RESOLVED TAG]="","",[FAT START]+SUMIFS('Logic & Lists'!$E4:E200,'Logic & Lists'!$A4:A200,[TYPE KEY],'Logic & Lists'!$C4:C200,"Internal Test Complete"))
FAT START = IF([RESOLVED TAG]="","",[DELIVERY]+SUMIFS('Logic & Lists'!$E4:E200,'Logic & Lists'!$A4:A200,[TYPE KEY],'Logic & Lists'!$C4:C200,"FAT Start"))
FAT COMPLETE = IF([RESOLVED TAG]="","",[FAT START]+SUMIFS('Logic & Lists'!$E4:E200,'Logic & Lists'!$A4:A200,[TYPE KEY],'Logic & Lists'!$C4:C200,"FAT Complete"))
DELIVERY = IF([RESOLVED TAG]="","",[ROS]+SUMIFS('Logic & Lists'!$E4:E200,'Logic & Lists'!$A4:A200,[TYPE KEY],'Logic & Lists'!$C4:C200,"Delivery"))
DAYS TO ROS = IF([ROS]="","",[ROS]-TODAY())
Note on A1: Optional input. Select or type the Tag No. from Product_Registry.
Note on B1: Optional input. Select or paste the item / description from Product_Registry. You can fill either A or B; columns C onward will populate automatically.

## Product_Registry
TAG NO. | DESCRIPTION | PRODUCT TYPE | CUSTOMER | CONTRACT SIGNED | ROS | CONTRACT NO. | SALES REF | PROJECT MANAGER | ENGINEER OWNER | PROCUREMENT OWNER | PRODUCTION OWNER | FAT OWNER | NOTES | LEVEL 1 PLAN | COMPONENTS PO PLAN | PRODUCTION START | DELIVERY | DAYS TO ROS
123456 | Chiller Water Unit | 冷水机组 | Sample Customer | 2026-03-10 | 2026-10-20 | CN-2026-001 | P84 Pilot | PM Owner | Engineering Owner | Procurement Owner | Production Owner | QA / FAT Owner | Pilot order seeded from uploaded sample tracker. | 2026-04-07 | 2026-03-23 | 2026-08-10 | 2026-10-17 | 63
Input sheet only — key each project here. Milestone preview columns O:S are read-only and come from Project_Tracker.
Formulas:
LEVEL 1 PLAN = IF([TAG NO.]="","",IFERROR(INDEX(Project_Tracker!$N2:N101,MATCH([TAG NO.],Project_Tracker!$AL2:AL101,0)),""))
COMPONENTS PO PLAN = IF([TAG NO.]="","",IFERROR(INDEX(Project_Tracker!$S2:S101,MATCH([TAG NO.],Project_Tracker!$AL2:AL101,0)),""))
PRODUCTION START = IF([TAG NO.]="","",IFERROR(INDEX(Project_Tracker!$T2:T101,MATCH([TAG NO.],Project_Tracker!$AL2:AL101,0)),""))
DELIVERY = IF([TAG NO.]="","",IFERROR(INDEX(Project_Tracker!$AA2:AA101,MATCH([TAG NO.],Project_Tracker!$AL2:AL101,0)),""))

## BOM_Tracker
Persistent BOM / Procurement Tracker
TAG NO. | DESCRIPTION | PRODUCT TYPE | ARRIVAL DEADLINE | SEQ | COMPONENT | LEAD TIME (DAYS) | LATEST PO / PREP BY | DAYS UNTIL NEED | URGENCY | ACTUAL PO DATE | ORDERED STATUS | VENDOR | PO NO. | NOTES | PROJECT MANAGER | PROCUREMENT OWNER
123456 | Chiller Water Unit | 冷水机组 | 2026-08-10 | 1 | 非防爆压缩机 Non Ex-proof COMPRESSOR | 45 | 2026-06-26 | -53 | OVERDUE |  | OVERDUE |  |  |  | PM Owner | Procurement Owner
123456 | Chiller Water Unit | 冷水机组 | 2026-08-10 | 2 | 防爆压缩机 COMPRESSOR | 90 | 2026-05-12 | -98 | OVERDUE |  | OVERDUE |  |  |  | PM Owner | Procurement Owner
123456 | Chiller Water Unit | 冷水机组 | 2026-08-10 | 3 | 蒸发器 EVAPORATOR | 90 | 2026-05-12 | -98 | OVERDUE |  | OVERDUE |  |  |  | PM Owner | Procurement Owner
123456 | Chiller Water Unit | 冷水机组 | 2026-08-10 | 4 | 冷凝器 CONDENSER | 90 | 2026-05-12 | -98 | OVERDUE |  | OVERDUE |  |  |  | PM Owner | Procurement Owner
123456 | Chiller Water Unit | 冷水机组 | 2026-08-10 | 5 | 底座框架 | 30 | 2026-07-11 | -38 | OVERDUE |  | OVERDUE |  |  |  | PM Owner | Procurement Owner
123456 | Chiller Water Unit | 冷水机组 | 2026-08-10 | 6 | 干燥过滤器 | 10 | 2026-07-31 | -18 | OVERDUE |  | OVERDUE |  |  |  | PM Owner | Procurement Owner
123456 | Chiller Water Unit | 冷水机组 | 2026-08-10 | 7 | 油分离器 | 10 | 2026-07-31 | -18 | OVERDUE |  | OVERDUE |  |  |  | PM Owner | Procurement Owner
123456 | Chiller Water Unit | 冷水机组 | 2026-08-10 | 8 | 阀件类 | 30 | 2026-07-11 | -38 | OVERDUE |  | OVERDUE |  |  |  | PM Owner | Procurement Owner
123456 | Chiller Water Unit | 冷水机组 | 2026-08-10 | 9 | 橡胶软接头 / RUBBER FLEXIBLE JOINT | 30 | 2026-07-11 | -38 | OVERDUE |  | OVERDUE |  |  |  | PM Owner | Procurement Owner
123456 | Chiller Water Unit | 冷水机组 | 2026-08-10 | 10 | 减震垫 / DAMPING PAD VCS | 30 | 2026-07-11 | -38 | OVERDUE |  | OVERDUE |  |  |  | PM Owner | Procurement Owner
123456 | Chiller Water Unit | 冷水机组 | 2026-08-10 | 11 | 铜管及配套弯头 | 10 | 2026-07-31 | -18 | OVERDUE |  | OVERDUE |  |  |  | PM Owner | Procurement Owner
123456 | Chiller Water Unit | 冷水机组 | 2026-08-10 | 12 | 仪器仪表 | 60 | 2026-06-11 | -68 | OVERDUE |  | OVERDUE |  |  |  | PM Owner | Procurement Owner
123456 | Chiller Water Unit | 冷水机组 | 2026-08-10 | 13 | 电箱（FUCA） | 45 | 2026-06-26 | -53 | OVERDUE |  | OVERDUE |  |  |  | PM Owner | Procurement Owner
123456 | Chiller Water Unit | 冷水机组 | 2026-08-10 | 14 | 填料函 | 30 | 2026-07-11 | -38 | OVERDUE |  | OVERDUE |  |  |  | PM Owner | Procurement Owner
123456 | Chiller Water Unit | 冷水机组 | 2026-08-10 | 15 | 电缆 | 30 | 2026-07-11 | -38 | OVERDUE |  | OVERDUE |  |  |  | PM Owner | Procurement Owner
123456 | Chiller Water Unit | 冷水机组 | 2026-08-10 | 16 | 保温材料 | 25 | 2026-07-16 | -33 | OVERDUE |  | OVERDUE |  |  |  | PM Owner | Procurement Owner
123456 | Chiller Water Unit | 冷水机组 | 2026-08-10 | 17 | 生产辅料 | 5 | 2026-08-05 | -13 | OVERDUE |  | OVERDUE |  |  |  | PM Owner | Procurement Owner
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
Formulas:
ARRIVAL DEADLINE = IF([TAG NO.]="","",INDEX(Project_Tracker!$T2:T101,INT((ROW()-6)/17)+1))
LATEST PO / PREP BY = IF([ARRIVAL DEADLINE]="","",[ARRIVAL DEADLINE]-[LEAD TIME (DAYS)])
DAYS UNTIL NEED = IF([LATEST PO / PREP BY]="","",[LATEST PO / PREP BY]-TODAY())

## Logic & Lists
Milestone Logic by Product Type | [5 empty] | Procurement Lead Times |  |  |  | Validation Lists |  |  | Selected Project Procurement Preview
[10 empty] | On Track | Pending | Note
Product Type | Seq | Milestone | Anchor / Basis | Offset (Days) | Note | Seq | Component | Lead Time (Days) | Remark | Watch | Y | Risk | Selected Tag | 123456 | ROS | 2026-10-20 | Latest Arrival | 2026-08-10
Default | 1 | Contract Signed | Input from registry |  | Input date | 1 | 非防爆压缩机 Non Ex-proof COMPRESSOR | 45 |  | At Risk | N | Delay | Description | Chiller Water Unit | Production Start | 2026-08-10 | Urgent Items | 17
Default | 2 | Level 1 Schedule | Contract Signed | 28 | 4 weeks after contract | 2 | 防爆压缩机 COMPRESSOR | 90 |  | Completed |  | Approval
Default | 3 | Input Frozen | Drawing Approval | -20 | 20 days before drawing approval | 3 | 蒸发器 EVAPORATOR | 90 | 冰轮的正常交期三个月 | Hold |  | Shipment
Default | 4 | Drawing Approval | BOM Pass to PR | -7 | 1 week before BOM pass to PR | 4 | 冷凝器 CONDENSER | 90 | 冰轮的正常交期三个月 |  |  |  | Component | Lead Time | Must Arrive By | Latest PO / Prep By | Days Until Need | Urgency
Default | 5 | BOM Pass to PR | Components PO Plan | -3 | 3 days before components PO plan | 5 | 底座框架 | 30 |  | Product types used in dropdown | Add new product types in col A |  | 非防爆压缩机 Non Ex-proof COMPRESSOR | 45 | 2026-08-10 | 2026-06-26 | -53 | OVERDUE
Default | 6 | PR Schedule | Components PO Plan | -7 | 1 week before components PO plan | 6 | 干燥过滤器 | 10 |  |  |  |  | 防爆压缩机 COMPRESSOR | 90 | 2026-08-10 | 2026-05-12 | -98 | OVERDUE
Default | 7 | Components PO Plan | Production Start | -140 | Long-lead buy plan | 7 | 油分离器 | 10 |  | 冷水机组 |  |  | 蒸发器 EVAPORATOR | 90 | 2026-08-10 | 2026-05-12 | -98 | OVERDUE
Default | 8 | Production Start | Production Complete | -45 | 45-day production window | 8 | 阀件类 | 30 | 非常见型号可延长到约3个月 | 冷水 |  |  | 冷凝器 CONDENSER | 90 | 2026-08-10 | 2026-05-12 | -98 | OVERDUE
Default | 9 | Production Complete | Internal Test Start | -3 | 3 days before internal test | 9 | 橡胶软接头 / RUBBER FLEXIBLE JOINT | 30 |  | ahu |  |  | 底座框架 | 30 | 2026-08-10 | 2026-07-11 | -38 | OVERDUE
Default | 10 | NOI Date | FAT Start | -28 | 4 weeks before FAT | 10 | 减震垫 / DAMPING PAD VCS | 30 |  |  |  |  | 干燥过滤器 | 10 | 2026-08-10 | 2026-07-31 | -18 | OVERDUE
Default | 11 | Internal Test Start | Internal Test Complete | -3 | 3 days before test complete | 11 | 铜管及配套弯头 | 10 |  |  |  |  | 油分离器 | 10 | 2026-08-10 | 2026-07-31 | -18 | OVERDUE
Default | 12 | Internal Test Complete | FAT Start | -2 | 2 days before FAT start | 12 | 仪器仪表 | 60 |  |  |  |  | 阀件类 | 30 | 2026-08-10 | 2026-07-11 | -38 | OVERDUE
Default | 13 | FAT Start | Delivery | -15 | 15 days before delivery | 13 | 电箱（FUCA） | 45 |  |  |  |  | 橡胶软接头 / RUBBER FLEXIBLE JOINT | 30 | 2026-08-10 | 2026-07-11 | -38 | OVERDUE
Default | 14 | FAT Complete | FAT Start | 7 | 7-day FAT window | 14 | 填料函 | 30 | CMP填料函约2个月 |  |  |  | 减震垫 / DAMPING PAD VCS | 30 | 2026-08-10 | 2026-07-11 | -38 | OVERDUE
Default | 15 | Delivery | ROS | -3 | 3 days before ROS | 15 | 电缆 | 30 |  |  |  |  | 铜管及配套弯头 | 10 | 2026-08-10 | 2026-07-31 | -18 | OVERDUE
Default | 16 | ROS | Input from registry |  | Input date | 16 | 保温材料 | 25 |  |  |  |  | 仪器仪表 | 60 | 2026-08-10 | 2026-06-11 | -68 | OVERDUE
冷水机组 | 1 | Contract Signed | Input from registry |  | Input date | 17 | 生产辅料 | 5 |  |  |  |  | 电箱（FUCA） | 45 | 2026-08-10 | 2026-06-26 | -53 | OVERDUE
冷水机组 | 2 | Level 1 Schedule | Contract Signed | 28 | 4 weeks after contract | [7 empty] | 填料函 | 30 | 2026-08-10 | 2026-07-11 | -38 | OVERDUE
冷水机组 | 3 | Input Frozen | Drawing Approval | -20 | 20 days before drawing approval | [7 empty] | 电缆 | 30 | 2026-08-10 | 2026-07-11 | -38 | OVERDUE
冷水机组 | 4 | Drawing Approval | BOM Pass to PR | -7 | 1 week before BOM pass to PR | [7 empty] | 保温材料 | 25 | 2026-08-10 | 2026-07-16 | -33 | OVERDUE
冷水机组 | 5 | BOM Pass to PR | Components PO Plan | -3 | 3 days before components PO plan | [7 empty] | 生产辅料 | 5 | 2026-08-10 | 2026-08-05 | -13 | OVERDUE
冷水机组 | 6 | PR Schedule | Components PO Plan | -7 | 1 week before components PO plan
冷水机组 | 7 | Components PO Plan | Production Start | -140 | Long-lead buy plan
冷水机组 | 8 | Production Start | Production Complete | -45 | 45-day production window
冷水机组 | 9 | Production Complete | Internal Test Start | -3 | 3 days before internal test
冷水机组 | 10 | NOI Date | FAT Start | -28 | 4 weeks before FAT
冷水机组 | 11 | Internal Test Start | Internal Test Complete | -3 | 3 days before test complete
冷水机组 | 12 | Internal Test Complete | FAT Start | -2 | 2 days before FAT start
冷水机组 | 13 | FAT Start | Delivery | -15 | 15 days before delivery
冷水机组 | 14 | FAT Complete | FAT Start | 7 | 7-day FAT window
冷水机组 | 15 | Delivery | ROS | -3 | 3 days before ROS
冷水机组 | 16 | ROS | Input from registry |  | Input date

## Comments_Log
Comments and Updates Log
Date | Tag No. | Owner | Update Type | Issue / Status | Comment | Next Action | Follow-up Date
2026-08-18 | 123456 | PM Owner | Note | Open | Pilot workbook created from current tracker logic. | Validate live workflow with next project. | 2026-08-25